## Task 2 - Requirements Reference
Accenture Online Voting Pilot for Australian Federal Government - User Stories for Ballot Related Functions
User Stories with Requirements Cross Reference
Epic Story |  | User Story |  |  | Future Use (Backlog Grooming and Iteration Planning
Epic Story # | Epic Story | User Story # | User Story | Requirement References | Level Of Effort | Priority | Test Criteria | Iteration
B1 | As a Voting Adminstrator I want to create a new ballot for an upcoming election | B1.1 | As a Ballot Creator I want to give my ballot and name and tag line and instructions so we can easily identify the different ballots and voters know how to use my ballot | 5.2.0
|  | B1.2 | As a Ballot Creator I want to specify a hierarchy so that eligible voters can be identified | 5.2.2
|  | B1.3 | As a Ballot Creator I want to add multiple choice selections so voters can see the candidates who have earned a spot on the ballot | 5.3.0
|  | B1.4 | As a Ballot Creator I want user should be able to toggle between edit and test modes. In test mode the user will be able to enter a ballot and its line items, subject to the rules established with all field validations active | 5.3.1
|  | B1.5 | As a Ballot Creator I want Ballot Creation and Edit Functions should employ a graphical use interface where the user sees what the ballot will look like while building it | 5.3.2
|  | B1.6 | As a Ballot Creator I want the user should be a function to copy an existing ballot or ballot template as the starting point for creating a new ballot | 5.3.3
|  | B1.7 | As a Ballot Creator I want the user should be a function to copy an existing ballot or ballot template as the starting point for creating a new ballot | 5.3.4
|  | B1.8 | As a Ballot Creator I want the design and functionality Similar to Surveymonkey or eBallot AND Each ballot, during creation and editing, should be restricted to a specific set of users | 5.3.5
|  | B1.9 | As a Ballot Creator I want Ballots should be data driven without any hardcoding. Ballots must support multiple choice with write-in options, Yes/No/Abstain/No Vote, and list of priorities voting (i.e., score multiple selections from a list) | 5.3.6
|  | B1.10 | As a Ballot Creator I want to make sure that Original Requirements from Susan are met and are fulfilled . | 5.3.7
B2 | As a Voting Adminstrator I want to obtain approval to publish my Ballot | B2.1 | As a Ballot Creator I want to notify Approvers so that my ballot can be approved | 5.2.5
|  | B2.2 | As an Approver I want to see and test the ballot so that I can approve and/or suggest revisions | 5.0.1
|  | B2.3 | As a Ballot approver I want Only authorised government employees should be able to access the Ballot Creation system, subject to current federal systems internal logon restrictions ,There should be an approval process established before a ballot can be published
|  | B2.4 | As a Ballot approver I want Participants from multiple federal, state, and/or local organisations should be able to create ballots and administer the election process
|  | B2.5 | As a Ballot approver I want There should an access list and audit trail, by user, of all changes made to a ballot (prior to publishing)
B3 | As a Voting Adminstrator I want to make my Ballot available to qualified Voters | B3.1 | As a Ballot Owner I want to prevent any further changes and indicate that it is in published state so the administator can publish the completed ballot | 5.1.3
|  | B3.2 | As a Ballot Owner I want to A graphical UI should be established that allows for multiple votes on a single ballot (e.g., elect several positions and/or vote on multiple questions)
|  | B3.2 | As a Ballot Owner I want to For multiple choice line items - there should be an optional flag (defaults to no) that allows multiple selections limited by an n to be entered into the line item UI
|  | B3.4 | As a Ballot Owner I want to Ballot Header should have an option to notify an eligible voter that the ballot is available and provide a direct line to the online ballot
|  | B3.5 | As a Ballot Owner I want to It would be great if a running count of "votes so far" could be shown during the voting process, not for all ballots/line items, but for some so that a user sees the current vote cound before voting